## Task Assignment
Feature | Description in Milestone II | Task highlight in Feature | Sponsers | Progress | Milestone 1 (Nov 11) | Milestone 2(Nov 18) | Milestone 3(Nov 25)
EF 1: Member Registration | Tackaholic system shall allow people to create their own account by use their email address, or just given the account name by themselves. Also system will allow user to create their own security question and answer. System also allow resisted user to update their information and change password after they login to the system. | 1. Login 2. Logout 3.Account settings 4.Register/Email | Ruiyun | 50% | UI design finished (output: html pages with bootstrap effect) | coding finished (output: working prototype with all features) | Integration finished
EF 2: Board Creation | Tackaholic system shall allow all registered user to create tacks or boards. User can upload their photos from local computer, or from other website. | 1. Create/Delete/Modify Board 2. Create/Delete/Modify Tack | Jing & Lan | 0%
EF 3: Member Interaction | Tackaholic system shall allow user to follow other people’s board or drag single photo from other people’s board and add to his own board. | 1. Follow boards 2. Follow user 3. Pin tacks | Yang & Junchen | 10%
EF 4: Tacks & boards Categorization | Tackaholic system shall allow user to choice a bunch of categories labels, however, only one category label can be assigned to a board. | 1. Build-in board category | Pouya & Nishant | 0%
EF 5: Board-based Images’ Collection | Tackaholic system shall allow user to view their boards and photos in waterfall effect. Also system allow user to access main content organized by theme which user will call as a board in the system. The board-based organization of a users' pin collection is the essential feature of our project. The theme can be an event or just a topic, such as wedding or food recipes sharing. | 1. Show public tacks 2. View tack detail | Ruiyun | 50%

## Mockups
https://drive.google.com/file/d/0B-Xvemn_Eo0nTVVhcEhQbHVMNHM/edit?usp=sharing

## Tables
https://drive.google.com/file/d/0B1dcPcw9ZfXFVzhFVTVZbGI1TUE/edit?usp=sharing
Tables
auth_user:
id
password
username
first_name
last_name
email
date_joined
Is_active
users_profile
id
user_id (foreign key: auth_user.id)
location
photo_id (foreign key: django_images_image.id)
email_alternative
core_board:
id
owner_id (foreign key: auth_user.id)
name
description
category_id (foreign key: core_category.id)
is_public (true/false)
core_category:
id
name
description
core_pin:
id
board_id (foreign key: core_board.id)
submitter_id (foreign key: auth_user.id)
url
origin
description
image_id(foreign key: django_images_image.id)
published